## Sheet1
Roles: 1 student 2 service provider 3 prospective service provider 4 admin 5 viewer
ID | STORY / FEATURE / REQUEST | Dependency | Story Points | Priority | Status | Success Demos | Failure Demos | Notes
1 | as a student I can register so that I can create an account |  | 5 | high |  | 1.click on register as a student in the home page 2.enter the needed information 3.press on register | - Student does not provide user name or password. -Password does not meet the above listed requirements. -Invalid email or mobile number.
1.1 | As a student I can login. | 1 | 5 | high |  | 1.i click on login as student 2. I enter the correct user name and password 3. press on login | Wrong user name-password combination.
1.2 | as a student I can edit my profile and interest tags | 1.1 | 5 | high |  | 1. I am already logged in and click on edit my profile 2. I modify the fields that I want 3. click on update | Student hasn't changed any data
1.3 | as a student I can rate and review service providers | 1.1 | 8 | low |  | 1. after viewing a service providers I click on rate and review 2. I write my review and click on the number of stars I want 3, I press submit review
1.4 | as a student I can view the home page | 1.1 | 3 | high |  | after logging in my homepage is displayed
1.5 | as a student my home page contains events or suggestions | 1.4 | 13 | high |  | events and suggestions are displayed in the homepage
1.6 | as a student I can search for service providers and other students |  | 8 | medium |  | 1. I click on search 2. I enter the name of the service provider or the student that I want to view 3. I click on search | student enters a non-existing service provider or student's name
1.7 | as a student I can view service providers and students | 1.6 , 1.4 | 3 | high |  | 1. I click on a service provider name or student in the news feed or after a search
2 | as a service provider I can register |  | 5 | high |  | 1.click on register as a service provider in the home page 2.enter the needed information 3.press on register | - Service provider does not provide user name or password. -Password does not meet the above listed requirements. -Invalid email or mobile number.
2.1 | as a service provider I can login | 2 | 5 | high |  | 1.i click on login as a service provider 2. I enter the correct user name and password 3. press on login | Wrong user name-password combination.
2.2 | as a service provider I can edit my profile and modify descriptive tags | 2.1 | 5 | high |  | 1. I am already logged in and click on edit my profile 2. I modify the fields that I want 3. click on update | Service provider hasn't changed any data
2.3 | as a service provider I can create events so that students can view them in their news feed | 2.1 | 3 | high |  | 1. I am logged in, I click on create an event 2. I enter its name and details 3. I click on create
2.4 | as a service provider I can view my rates and reviews | 2.1 | 3 | low
2.5 | as a service provider I can search for other service providers and students |  | 8 | medium |  | 1. I click on search 2. I enter the name of the student or service provider that I want to view 3. I click on search | Service provider enters a non-existing service provider's or student name
2.6 | as a service provider I can view other service providers and students | 2.5 | 5 | medium |  | 1. I click on a service provider or a student name after a search
3 | as a prospective service provider I can fill a form so that I can apply |  | 5 | high
4 | as an admin I can login |  | 5 | high |  | 1.i click on login in the admin homepage 2. I enter the correct user name and password 3. press on login | Wrong user name-password combination.
4.1 | as an admin I can search for service providers | 4 | 5 | medium |  | 1. I am logged in, I click on service providers list 2. I enter the filter that I want to apply 3. I click on search | admin not logged in
4.2 | as an admin I can view service providers and students | 4.1 | 3 | medium |  | 1. I am logged in, i click on a service provider or a student name after a search | admin not logged in
4.3 | as an admin I can remove any service provider or student | 4.2 | 3 | medium |  | 1. I am logged in ,after viewing a service providers or a student I click on remove | admin not logged in
4.3 | as an admin I can view reports | 4 | 3 | medium
4.4 | as an admin I can accept or reject prospective service providers | 4 | 5 | high |  | 1.i am logged in, I click on view applications 2. I select an application 3. I click on accept or reject | admin not logged in
4.5 | as an admin I can view events created by service providers | 4 | 3 | low
5 | as a viewer I can view service providers |  | 3 | low |  | 1. I click on a service provide name after a search
5.1 | as a viewer I can search for students and service providers |  | 5 | low |  | 1. I click on search 2. I enter the name of the student or service provider that I want to view 3. I click on search | Service provider enters a non-existing service provider's or student name